## Sheet1
Activity/function | Responsible party/solution | Must be ready by | Must start work by
CMMI Model Operational Planning
Start a Model Plan in MINT | Model Team
Contractor support prior to clearance We recommend discussing pre-clearance contractor support needs during your 2-pager or 6-pager review with the CMMI Front Office (FO), as CMMI FO will need to approve this request. | ARDS (available through BSG/DCCS), MITRE (available through PPG)
2-pager review with CMMI FO | Model Team
Conduct kick-off meeting | MINT Team
6-pager review with CMMI FO | Model Team
Perform iterative analysis of IT plans | Model Team, MINT Team
Draft IT cost estimates | MINT Team
Draft implementation cost estimates | BSG Budget Team
Draft evaluation cost estimates | Evaluation
Draft learning cost estimates | LDG
Draft high-level project plan (upon request) | MINT Team
Draft Innovation Center Investment Proposal (ICIP) | Model Team, MITRE (if this support is requested/approved by CMMI FO)
Collect/review and distribute deliverables to model team, SMEs, and stakeholders | MINT Team
Deliver final version of all BSG deliverables to model team, SMEs, and stakeholders | MINT Team
CMMI Internal Clearance Process
Submit documents to clearance designees (CMMI Clearance form) | MINT Team
Provide Model with complete CMMI clearance | CMMI designees and reviewers
ICIP Budget Model Teams will meet with CMMI FO to review the ICIP cost estimates | CMMI Deputy Director of Operations
Quality | Supervisory Medical Officer
Financial Methodology | Division of Data Analytics Representative
QPP Status | QPP SME
Technology | Chief Technology Officer or SME
Strategy | Chief Strategy Officer
Clearance of Documents
Submit Model documents completed/signed form and model clearance package to Executive Operations Staff (EOS) | Model Team
ICIP | Model Team and MITRE write, EOS clears
Cooperative Agreement | Legal Vertical writes, Office of the General Council (OGC) approves, EOS clears
Participation Agreement | Legal Vertical writes, OGC approves, EOS clears
Terms & Conditions | Legal Vertical writes, OGC approves, EOS clears
Notice of Proposed Rulemaking (NPRM) (mandatory models only) | OGC writes, EOS clears, staff publishes, and OGC processes and responds to comments
Final Rule (mandatory models only) | EOS clears, staff publishes
Announcement materials | Model Team, Front Office, PPG Division of Stakeholder Engagement and Policy (DSEP), Office of Communications (OC)
Legal
Fraud, Waste, Abuse Waivers | Federal Waiver Team writes, Office of Inspector General (OIG) and CM approve
Program/Payment Waivers (included in ICIP) | CMMI, OGC
Medicaid Waivers/State Plan Amendments | Center for Medicaid and CHIP Services (CMCS), OGC
Request for Applications (RFA) or Notice of Funding Opportunity (NOFO) | Model Team writes, OGC approves
Participants
Obtain an application support contractor (as necessary if there are large volumes of applications) | RMADA
Recruit participants | GrantSolutions, CMS Qualtrics, Salesforce LOI, Salesforce RFA
Review and score applications | GrantSolutions, Salesforce ARS
Establish a benchmark with participants | CCW, IDR
Provide participant access to model platforms | Innovation Center (IC) Landing Page
Communicate with participants | Outlook Mailbox, GovDelivery, Salesforce POST
Vet providers for program integrity | CPI Vetting
Sign participation agreements | 4i, through a contractor
Manage Part C/D enrollment (MAPD models only) | MARx
Review and collect plan bids (MAPD models only) | HPMS
Update the plan’s contract (MAPD models only) | HPMS
Helpdesk support | CBOSC, through a contractor
Develop methodologies for providers and beneficiaries as needed | Implementation contractor
Manage provider overlaps | MDM
Manage beneficiary overlaps | MDM
Model Operations
Decide on contracting strategy | Division of Central Contracts Services (DCCS)
Acquire implementation contractor | DCCS, Office of Acquisition and Grants Management (OAGM)
Utilize quality measures development contractor | Quality Vertical
Collect quality measures data | CCSQ contracts and systems, HDR, Patient Activation Measure (PAM)
Innovative Design, Development, and Operations Contract (IDDOC) support | 4i, ACO-OS
Claims-based measures | CCW, IDR
Quality performance scores | Existing CMS data and process, HDR, other new process
Data to monitor the model | CCW, CDX, HDR, IDR, Salesforce POST, another contractor
Data to support model evaluation | CCW, CDX, HDR, Salesforce POST
Send reports/data to participants | 4i, BCDA, CDX, CMS Box, eDFR, EFT, RMADA, Salesforce POST, internal staff
Participate in CMMI data sharing | CMMI Analysis & Management System (AMS)
Process participant appeals | Legal Vertical
Payment
Adjust how FFS claims are paid | Shared Systems / CR, HIGLAS
Manage FFS excluded payments | Shared Systems / CR
MAPD payments | MAPD Systems / CR
Make non-claims based payment | APPS, HIGLAS, IPC
Compute shared savings payment | RMADA
Recover payments | APPS, IPC, Shared Systems
Learning & Diffusion
Develop a learning strategy | LDG
Educate beneficiaries | LDG
Acquire a learning contractor | RMADA, a cross-model contract
IT platform for learning | Salesforce CONNECT
Participant-to-participant collaboration | Salesforce CONNECT
Evaluation
Acquire an evaluation contractor | RMADA
Obtain data access for evaluation contractor | CCW